## Sheet1
S/N | Task | Date | Li Chengzhen(hrs) | Lin Yuxiang(hrs) | Remarks
1 | Skylab | 2023-05-08 | 1 | 1 | Set the password of Skylab and log in
2 | Programme overview | 2023-05-09 | 2 | 2 | 1. Attended programme overview 2. Meet with advisor
3 | 1. Liftoff 2. Animation | 10 May to 15 May | 16 | 14 | 1. Completed poster and video of liftoff 2. Installed unity 3. Named the game 4. Drew the idle, walk and run animations of character
4 | 1. Programing 2. Animation 3. Github | 16 May to 19 May | 12 | 18 | 1. Learned unity from online courses 2. Drew the dash, stop, jump and attack animations of character 3. Set up Github group
5 | 1. Programing 2. Sprite | 20 May to 23 May | 18 | 16 | 1. Learned unity from online courses 2. Transfered the format of idle, walk, run, dash, stop, jump and attack animations to sprites 3. Rendered idle, walk and run sprites
6 | Milestone 1 | 24 May to 26 May | 10 | 9 | 1. Updated and replaced all the sprites of character 2. Completed the project poster
7 | 1. Milestone 1 2. Programing | 27 May to 29 May | 12 | 14 | 1. Completed the project video, README and project log of milestone 1 2. Deleted the delayed jump 3. Jumping animation smoothing 4. Drew the crouch animation of player
8 | 1. Programing 2. Animation | 30 May to 2 June | 10 | 18 | 1. Added attack action of player 2. Drew the animation of a new enemy Axe 3. Implemented idle state and patrol state of Axe 4. Implemented hurt state and dead state of player 5. Fixed plenty of bugs of player attack
9 | 1. Programing 2. Animation | 3 June to 12 June | 34 | 0 | 1. Drew the animation of a new enemy Spear 2. Implemented idle state and patrol state of Spear 3. Implemented hurt state of two enemies 4. Replaced the walking animation of player 5. Added attack collider boxes 6. Drew the attack animation of Axe 7. Drew the hurt and dead animations of player
10 | 1. Programing 2. Animation | 13 June to 15 June | 6 | 9 | 1. Implemented encounter state of Axe 2. Drew all after-attack animations of each segment of attack 3. Implemented interruption of each segment of attack 4. Implemented chase state of two enemies
11 | Programing | 16 June to 19 June | 8 | 11 | 1. Added health bar of player 2. Implemented camera following 3. Fixed many bugs of enemies, made their action logic more resonable
12 | 1. Programing 2. Map | 20 June to 24 June | 10 | 14 | 1. Implemented camera shake 2. Added dash skill to the player 3. Made the first map
13 | Milestone 2 | 25 June to 26 June | 6 | 6 | Completed the project video, project poster, README and project log of milestone 2
14
15
16
17