## Sheet1
S/N | Task | Date | Li Chengzhen(hrs) | Lin Yuxiang(hrs) | Remarks
1 | Skylab | 2023-05-08 | 1 | 1 | Set the password of Skylab and log in
2 | Programme overview | 2023-05-09 | 2 | 2 | 1. Attended programme overview 2. Meet with advisor
3 | 1. Liftoff 2. Animation | 10 May to 15 May | 16 | 14 | 1. Completed poster and video of liftoff 2. Installed unity 3. Named the game 4. Drew the idle, walk and run animations of character
4 | 1. Programing 2. Animation 3. Github | 16 May to 19 May | 12 | 18 | 1. Learned unity from online courses 2. Drew the dash, stop, jump and attack animations of character 3. Set up Github group
5 | 1. Programing 2. Sprite | 20 May to 23 May | 18 | 16 | 1. Learned unity from online courses 2. Transfered the format of idle, walk, run, dash, stop, jump and attack animations to sprites 3. Rendered idle, walk and run sprites
6 | Milestone 1 | 24 May to 26 | 10 | 9 | 1. Updated and replaced all the sprites of character 2. Completed the project poster
7 | 1. Milestone 2 2. Programing | 27 May to 29 May | 12 | 14 | 1. Completed the project video, README and project log of milestone 1 2. Deleted the delayed jump 3. Jumping animation smoothing 4. Drew the crouch animation of character
8 |  |  | 71 | 74
9
10
11
12
13
14
15
16
17